## Sheet1
No | Name | Answer
1 | Why should the Po be present at the daily scrum? | He/she doesn't need to be there
2 | Every scrum team must have a Product owner and scrum master | True. Outcomes are affected by their participation and availability
3 | The PO must ship each sprint increment | D. when it makes sense
4 | A scrum master is working with a dev team that has members in different physical locations...(for ex, set up conference calls...) what action should the scrum master take : | Allow the DEV team to self manage and determine for itself what to do
5 | What is included in the sprint backlog? | Tasks
6 | What is the main reason for the scrum master to be at the daily scrum? | He or she does not have to be there; he or she only has to ensure the development team has a daily scrum
7 | Which technique is the least productive way for the scrum master to ensure that the DEV team communicates effectively with the PO. | Act as a go between for them
8 | Why does a dev need a sprint goal? | The DEV team is more focused with ha common yet specific goal
9 | The Development Team should not be interrupted during the Sprint. The Sprint Goal should remain intact. These are conditions that foster creativity, quality and productivity. Based on this, which of the following is FALSE? | The sprint backlog and its contents are fully formulated in the sprint planning meeting and do not change during the sprint.
10 | A scrum master is introducing scrum to a new development team. The development team has decided that a retrospective is unnecessary. What action should the scrum master take? | Begin facilitating productive and useful retrospective
11 | The timebox for the complete sprint planning meeting is? | 8 hours for a monthly srpint. For shorter sprint it is usally shorter
12 | Which two things does the dev team not do during the first sprint | A .Develop a plan for the rest of the project B. Nail down the complete achitecture and infrastructure
13 | When can a dev team cancel a sprint | It can't only PO can cancel sprints
14 | Which three of the following are feedback loops in scrum? | Daily scrum Sprint reveiew Sprint retrospective
15 | The product owner makes sure team selects enough from the product backlog for a sprint to satisfy the stakeholders | FALSE
16 | When many scrum team are working on the same product, should all of their increments be integrated every sprint | Yes, otherwise the product owners (and stakeholders) may not be able to accurately inspect what is done
17 | 50. what are two responsibilities of testers in a dev team? | A. everyone in the dev team is responsible for quality D. scrum has no "tester" role
18 | A Sprint Retrospective should be held: | D. At the end of each sprint
19 | How many hours per day should a person on a scrum team work | A. At a sustainable pace, usually 7-8 hours per day.
20 | Which two things does a scrum team to do if the development team does not have the engineering tools and infratructure to completely finish any product backlog items? | A. Asks the DEv team to do the bes it can on each product backlog item it selects D. Has the dev team improve its skills, tools and infrastructure over time and adjust the definition of "done" accordingly
21 | The PO remains distant. he/she handed over the required Product backlog for the sprint but is not collaborating with the DEV team during the sprint. What are valuabe actions for a scrum master? | A. Coach the PO in the values of scrum and incremental delevery B. Bring up the problem in the sprint retrospective
22 | When is a sprint over? | D. When the time box expires
23 | What are three benefits of self organization | A. Increased self accountability B. Increased commitment C. Increased creativity
24 | An organization has decided to adopt scrum, but management want to change the terminology to fit with terminology already used. what will likely happent if this is done? | All answers apply
25 | An abnormal termination of a sprint is called when? | B.when the po determines that it makes no sense to finish it
26 | What activities would a PO typically undertake in the phase between the current sprint review meeting and the next sprintt's sprint planning. | Refining the product backlog
27 | What does it mean for a Development team to be cross functional? | C. The development team includes cross-skilled individuals who are contribute
28 | Which are not appropriate topics for discussion in a sprint retrospective | D. Sprint backlog for the next sprint E. The value of work currently represented in the product backlog
29 | THe CEO asks the dev team to add a "very important item to the current sprint. what should the dev team do? | C. Inform the PO so he/she can work with the CEO
30 | As the Sprint Planning meeting progresses, the Development Team sees that the workload is greater than they can handle. Which two are valid actions? | D. remover or change selected product backlog items E. The development team ensures that the product owner is aware, starts the sprint and monitors progres
31 | What is the primary way a scrum master keeps a development team working at its highest level if productivity? | D. By facilitating development team decisions and removing impediments.
32 | Who has the final say on the order of the product backlog? | B. The product owner
33 | Which of the following best describes an increment of working software | A. Additional features in a useable states that complement those delivered in previous iterations
34 | The maximum lenght of the sprint review is | E. 4 Hours for a monthly sprint. for shorter sprints it is usually shorter
35 | A scrum Master is keeping a list of open impediments, but it is growing and he/she has been able to resolve only a small portion of the impediments. which three (3) techniques would be most helpful in this situation? | B. Alert management to the impediments and their impact C. Consult with the development team F. Prioritize the list and work on them in order.
36 | Sprint burdown charts are an efficient traking tool because they show: | C. An estimate of the total work remaining for the sprint
37 | When a Development Team determines that it has over committed itself for a sprint, who has to be present when reviewing and adjusting the sprint work selected | C. The product owner and the Development team
38 | Which phrase best describes a PO | Value optimizer
39 | The sprint goal is a result of sprint planning, as is the sprint backlog. | TRUE
40 | Scrum is a methodology that tells in detail how to build software incrementally | B. False
41 | If burndown charts are useds to visualize progress, what do they track? | A. Work remainning across time
42 | What two things might a Development team do when having trouble delivering a working increment? | C. collaborate with the PO to determine what is possible and acceptable D. Complete what it can and discuss undone work at the sprint review
43 | Which does a self organizing team choose? | How to best accomplish its work
44 | How much work must a dev team do to a product backlog item it selects for a sprint | B As much as it has told the PO will be done for every product backlog item it selects in conformance with the definition of "Done"
45 | What are the benefits of including testing within the sprint's development activities? | A. The increment is closer to being potentially releasable B. Transparency of the increment is increased C. The increment is likely to be more complete.
46 | When is a product backlog item considered complete? | The item has no work remaining that must still be done before it can be used by its end user
47 | How is management external to the scrum team involved in the daily scrum? | A. The Development team self manages and is the only management required at the daily scrum. all others cannot participate
48 | The product backlog is ordered by: | C. Whatever is deemed most appropriate by the PO
49 | A property functioning scrum team will have at least one release sprint and may well have serveral | True/False(*)
50 | How much of the sprint backlog must be defined during planing meeting | D. Enough so the development team can create its best forecast of what it can do and to start the first several days of the sprint
51 | Who should know the most about the progress toward a business objective or a release, and be able to explain the alternatives most clearly. | C. The Product owner
52 | Who determines how work is performed during the sprint? | A. The Development Team
53 | Scrum Master is a "management" position? | A.True
54 | who must do all the work to make sure product Backlog items conform to the Definition of"Done?" | A. The Development Team
55 | The Development Team should have all the skills needed to : | C. Turn the product backlog items it selects into an increment of potentially shippable product functionality
56 | When many Development teams are working on a single product, what best describes the definition of "Done"? | A. All Development teams must have a definition of "Done" that makes their combined work potentially releasable
57 | The definition of "done" is used to: | A. Create a shared understanding of when work is complete B. Describe the work that must be done before the sprint can end C. increase transparency
58 | While under development, the environment in which a product will be used changes and emerge. what is the effect on the product backlog | D. It is archived and a new product backlog is created to take its place
59 | As scrum team mature, it is expected that the following decision is likely to be taken: | B. They will improve their definition of "Done" to include more stringent
60 | Which answer best describes the topics covered in sprint planning? | D. What can be done and how to do it.
61 | When does the next sprint begin? | Immediately after the conclusion of the previous sprint
62 | Who is responsible for engaging the stakeholders? | E. The PO